## Table 1
Test Plan – Healthify Health Management System 1. Document Information
2. Introduction This document describes the manual testing strategy for the Healthify web application. Healthify is a health record management system built for Sri Lankan patients and doctors, developed using React, JavaScript, and Tailwind CSS (frontend) with a REST API backend. 3. Objectives of Testing Verify that all user interfaces function as designed Conflrm that form validations work correctly Ensure that role-based access control is enforced (Patient / Doctor / Admin) Validate that patient health data is secure and not accessible to unauthorized users Conflrm that navigation flows work end to end 4. Testing Scope Welcome / Home page Login page (all three roles) Patient registration form (all steps) Doctor registration form (both pages) Patient dashboard features Doctor dashboard features Admin dashboard features Password reset flow Logout functionality UI responsiveness (mobile, tablet, desktop) Basic security checks (unauthorized access, role routing)
5. Test Approach

## Table 2
Type of Testing: Manual Black-Box Testing Testing will be done by: Developers Environment: Local development environment Browser: Google Chrome (latest version) Tools used: Browser (Chrome) Chrome DevTools (Console + Network tab) Postman (for API testing ) Google Sheets (for recording test results) 6. Test Environment
7. Roles Used in Testing
Role | Test Credentials
Patient | thathsaraabhi232@gmail.com / Abhi03cs
Doctor (Approved) | indikamad.i@gmail.com / Indika@123
Doctor (Pending) | pending@test.com / Test@1234
Admin | admin@healthify.com / Admin@1234
Disabled Account | disabled@test.com / Test@1234

## Table 3
8. Test Modules
9. Entry Criteria (When to Start Testing) Frontend dev server runs without errors Backend API is running and connected to the database At least one test account for each role is created in the database All pages mentioned in scope are accessible via routes 10. Exit Criteria (When Testing is Complete) All test cases have been executed All High priority test cases pass No Critical or High severity bugs remain open Test Summary Report is completed